## Task management
Project FBD
Task management
ID | Problem | Analysis | Action | Status | PIC | Start date | End date | Note
| Document: Manage versions of document, updated time, updated by who?... |  | Create Google project on Google group or Turtoise | In progress | ChinhPLQ | 23/10/2010 | 30/10/2010
| Outline Requirement document, làm sample 1 cái requirement: |  | Create outline for SRS, build an example for a requirement | In progress | LongNT | 23/10/2010 | 30/10/2010
| Design DB | The database given from customer for reference is not clear and normalized | - Study and understand the structure of that DB, then - Cleanse and normalize it to build a DB for module A | In progress |  | 23/10/2010 |  | All members will pic this task, deadline is not set
| QA framework: Define Template: |  | Define template for all document needed for managing task: TC, bug, risk, task, meeting minute | In progress | GiangTTH | 23/10/2010 | 30/10/2010 | PIC: Giang + Thảo, tham khảo temp của FSOFT

## Data (hidden)
Status | Open | PIC | LongNT
| In progress |  | ChinhPLQ
| Pending |  | GiangTTH
| Done |  | LyDM
| Close |  | ThaoPTP